## Sheet1
Task | Start Date | End Date | Duration
Finalise ML models, parameters, and datasets | 2025-08-01 | 2025-08-07 | 6
Literature review of CA and optimisation (Milestone: Detailed Research Plan Completed) | 2025-08-08 | 2025-08-28 | 20
Design CA architecture & evolution rules | 2025-08-28 | 2025-09-07 | 10
Implement Gradient Descent baseline code | 2025-09-07 | 2025-09-13 | 6
Implement CA-based optimiser code (Milestone: Functional Codebase Ready) | 2025-09-13 | 2025-10-03 | 20
Conduct experiments and data collection | 2025-10-03 | 2025-10-18 | 15
Analyse and interpret results (Milestone: All Data Analysed) | 2025-10-18 | 2025-11-01 | 14
Write dissertation report | 2025-11-01 | 2025-12-01 | 30
Final review and proofreading (Milestone: Final Submission) | 2025-12-02 | 2025-12-04 | 2
45870 | 45995